## Slide 1: Phases of Acquisition Process
Determine a Need
• Identify service/product desired
2 Assemble Acquisition Team
        • PO, CO, CS, AO, OGC, program team
3 Draft Statement of Work
    • Salient Characteristics
    • Deliverables
    • Delivery Schedule
    • Special Requirements,
    • Mandatory & Standard Evaluation Criteria
    • Technical Proposal Instructions
4 Develop an Acquisition Plan (AP/AS)
    • Identify Sources
    • Conduct Market Research
    • Construct IGCE
    • Availability of Commercial Item
    • Competition Method (RFP)
    • Select contract type (FP/CR)
    • Select TEP members
    • Other issues (warranty/options)
5 Meet with Acquisition Team to review Draft SOW & Draft AP/AS
    • Make corrections
Finalize SOW & Acquisition Plan
Present Final SOW and Final AP/AS to the Contracting Officer
1 Draft and Post Final Synopsis
    • FedBizOpps.gov
2 CO drafts and finalizes RFP for internal review
3 Post Solicitation/RFP (request for proposal)
    • FedBizOpps.gov
4 Answer Questions submitted by Potential Offerors
5 All Communication goes through the Contracting Officer
6 Amend solicitation/RFP
7 Receive & Record Proposals
8 Distribute Proposals to TEP Team
9 CO reviews business proposals and begins cost and price analysis
10 Hold TEP
    • Score Proposals to evaluation criteria
    • Develop technical score
    • Vote acceptable/Unacceptable
    • TEP report to CO
11 Determine Competitive Range
12 Submit Questions to Offerors in Competitive Range. Notify those excluded. May conduct debriefings.
13 Review Answers to Questions
14 Negotiate, win-win solution
15 Might need a revised proposal
16 Request and Receive Final Proposal Revisions (FPR)
17 Make a Source Selection
18 Award Contract
1 Copy of Contract to Contracting Officer Representative (COR)
    • Highlight PO duties
2 Post Award Kick-Off Meeting
3 Read & Review Monthly Progress Reports
4 Inspect and Accept Product or Service
5 COR reports issues/concerns/problems to Contracting Officer
6 Execute Contract Modifications
    • Unilateral or Bilateral
    • Exercise options
7 Review & Approve Invoices
8 Maintain Deliverables of Contractor
9 Perform Site-visits to Contractor
10 Perform Annual Evaluation of Contractor’s Performance
11 Assist in Contract Closeout
* On average Contracts have a period of performance of 5 years
* Some have 1 base year + up to 4 option years (could have between 2–5 years total)
Acquisition Planning (AP)/ Acquisition Strategy (AS)
RFP/Solicitation
Contract Administration